Performance in initiating Clinical Trials Q4 – 2020/21 (HRA APPROVAL)

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REC | IRAS Number | Name of Trial | First Patient Recruited | Date First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed by Sponsor | Date Site Confirmed | Date Site Ready to Start | Reason for delay | Comments | Reason for Delay corresponds to |
|

|  |
| --- |
| 19/LO/1354 |

 |

|  |
| --- |
| 262807 |

 | OPTYC Online PTSD Treatment for Young People and Carers – RCT | Yes | 24/082020 | 04/12/2019 | 01/07/20 | 07/01/2020 | 17/07/2020 | 17/07/2020 | 07/07/2020 | No patient consented |  |  |
|

|  |
| --- |
| 19/LO/1667 |

 | 271363 | (NIDUS) for family carers and people living with dementia in their own homes: A randomised controlled trial | Yes | 20/09/2020 | 26/06/2020 | 23/07/2020 | 13/01/2020 | 31/07/2020 | 31/07/2020 | 31/07/2020 |  |  |  |
| 20/SC/0281 | 281235 | The SleepWell Trial |  Yes | 30/11/2020 | 01/09/2020 | 18/09/2020 | 19/08/2020 | 29/09/2020 | 29/09/2020 | 29/09/2020 | No patient consented |  |  |
|

|  |
| --- |
| 20/SC/0158 |

 |

|  |
| --- |
| 281958 |

 | Platform Randomised trial of INterventions against COVID-19 In older people | Not yet |  | 06/08/2020 | 18/09/2020 | 26/03/2020 | Not yet | 22/09/2020 | 22/09/2020 | Sponsor Delays/Staff availability issues | Waiting for sponsorship confirmation | Both |
| 20/HRA/4431 | 288074 | Child Anxiety Treatment in the context of COVID-19 (Co-CAT): | Yes | 31/01/2021 | 06/08/2020 | 24/11/2020 | 04/09/2020 | 27/11/2020 | 27/11/2020 | 27/11/2020 |  |  |  |
| 20/WA/0206 | 281255 | Watch Study | Yes | 31/12/2020 | 28/05/2020 | 23/11/2020 | 30/09/2020 | 30/11/2020 | 30/11/2020 | 30/11/2020 |  |  |  |