Performance in initiating Clinical Trials Q1 - 2019/20 (HRA APPROVAL)

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REC | IRAS Number | Name of Trial | First Patient Recruited | Date First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed by Sponsor | Date Site Confirmed | Date Site Ready to Start | Reason for delay | Comments | Reason for Delay corresponds to |
| 16/NW/0389 | 196438 | Effective Home Support in Dementia Care: Project 2.1 Dementia Early Stage Cognitive Aids New Trial (DESCANT) | Yes | 13/11/18 | 02/05/18 | 28/09/18 | 20/06/16 | 23/10/18 | 17/10/18 | 17/10/18 |  |  |  |
| 18/SC/0164 | 240881 | Imagery Based Emotion Regulation for Bipolar Disorder | Yes | 28/01/2019 | 09/02/2018 | 05/09/2018 | 03/05/2018 | 01/10/2018 | 01/10/2018 | 10/10/2010 | No patient consented |  | Neither |
| 18/LO/0362 | 238744 | Early Youth Engagement in first episode psychosis (EYE-2) RCT | Yes | 26/11/2018 | 17/10/2018 | 08/11/2018 | 11/05/2018 | 26/11/2018 | 26/11/2018 | 26/11/2018 |  |  |  |
| 19/SC/0075 | 256895 | The gameChange Trial: A randomised controlled trial testing automated virtual reality cognitive therapy for patients with fears in everyday social situations | No | Not yet | 03/05/2019 | 30/05/2019 | 07/05/2019 | 08/07/2019 | 08/07/2019 | 08/07/2019 | No patients consented | Currently still within 30 day recruitment window | Neither |
| 18/YH/0499 | 258585 | Smoking Cessation Intervention for severe Mental Ill Health Trial (SCIMITAR Plus): | Yes | 19/04/2019 | 16/04/2019 | 16/04/2019 | 25/01/2019 | 18/04/2019 | 18/04/2019 | 18/04/2019 |  |  |  |